## Sheet1
Day | Task | Status | Comments | Priority
Day 1 | Research the basics of DNA sequencing (SNPs, genetic markers). | Completed
Day 2 | Explore DNA file formats and download a sample SNP dataset. | Completed
Day 3 | Install Python, Flask/Django, MongoDB, and libraries (pandas, numpy, etc.). | Completed | flask, scikit-learn, pandas, numpy, biopython and matplotlib were downloaded.
Day 4 | Set up virtual environment and verify Flask/Django installation. | Completed
Day 5 | Research existing DNA-based health prediction tools and draft key features. | Completed
Day 6 | Draft project feature list and UI wireframe. Read about backend concepts. Learn HTTP methods (GET and POST). Create and modify Flask routes. Create an HTML form and handle form submissions in Flask. Push the updated project to GitHub. Learn about Flask | Completed
Day 7 | Rest or review what you’ve learned; prep for backend dev. | To Do
Day 8 | Create Flask/Django project and set up basic routes. | To Do
Day 9 | Build file upload endpoint to accept DNA raw files. | To Do
Day 10 | Write DNA parsing script to extract SNP data. | To Do
Day 11 | Refine parsing to extract key SNPs linked to health traits. | To Do
Day 12 | Build REST API to handle DNA uploads and send parsed data. | To Do
Day 13 | Set up MongoDB and create user DNA data storage. | To Do
Day 14 | Integrate parsing feature with MongoDB database. | To Do
Day 15 | Research datasets for SNPs and health outcomes. | To Do
Day 16 | Preprocess dataset (handle missing data, normalize SNP values). | To Do
Day 17 | Implement basic ML model (logistic regression) using Scikit-learn. | To Do
Day 18 | Improve model with other algorithms (e.g., decision tree). | To Do
Day 19 | Fine-tune hyperparameters and evaluate model accuracy. | To Do
Day 20 | Save trained model and integrate it with Flask/Django backend. | To Do
Day 21 | Test end-to-end flow: Upload DNA -> Parse SNP -> Predict health risks. | To Do
Day 22 | Set up React project and create basic components (Navbar, Dashboard). | To Do
Day 23 | Design and implement file upload UI in React. | To Do
Day 24 | Create dashboard layout to display health insights. | To Do
Day 25 | Implement API calls from React frontend to Flask/Django backend. | To Do
Day 26 | Display parsed DNA data and health predictions in the dashboard. | To Do
Day 27 | Add charts/graphs to visualize health risks. | To Do
Day 28 | Review and debug frontend-backend integration. | To Do
Day 29 | Implement user authentication (login/signup) in Flask/Django. | To Do
Day 30 | Create user profile page to display past DNA analyses. | To Do
Day 31 | Add personalized nutritional advice feature based on genetic data. | To Do
Day 32 | Implement data security measures (e.g., encrypting DNA data). | To Do
Day 33 | Set up form validation and error handling on frontend. | To Do
Day 34 | Test user authentication and profile management features. | To Do
Day 35 | Write unit tests for Flask/Django backend. | To Do
Day 36 | Perform frontend testing using Jest/React Testing Library. | To Do
Day 37 | Conduct integration tests for end-to-end functionality. | To Do
Day 38 | Deploy Flask/Django app on Heroku or AWS. | To Do
Day 39 | Deploy React frontend on Vercel or Netlify. | To Do
Day 40 | Set up SSL, custom domain, and production configurations. | To Do
Day 41 | Test deployed app and fix any deployment issues. | To Do
Day 42 | Write project documentation (setup instructions, API docs). | To Do
Day 43 | Create professional README file for GitHub. | To Do
Day 44 | Record demo video showcasing app’s features. | To Do
Day 45 | Create slide deck for presenting project to recruiters. | To Do
Day 46 | Share project on LinkedIn, GitHub, and other platforms. | To Do
Day 47 | Gather feedback and review project with peers. | To Do
Day 48 | Make final adjustments based on feedback. | To Do
Day 49 | Celebrate your completed project and reflect on lessons learned! | To Do